## Sheet1
S N | Name Of Work | Alloc ation | Current Cost (In Cr.) | Status | Currently with | Pending Since | Present Status
1 | Whitefield-Major Upgradation/ Modernisation of infrastructure at SGWF goods shed. | CAP | 75.87 | Shortlisted | ED/SD&T | 2024-07-08 | with RB for Sanction
2 | KYATSANDRA~~Major upgradation/ modernisation of infrastructure at KDAG goods shed | CAP | 21.75 | Shortlisted | ED/SD&T | 23-12-2024 | with RB for Sanction
3 | Bangarapet - SBC Division - Provision of Quick coach watering system for all 6 platforms at BWT station . | Cap | 25119 | Shortlisted | Sr.DFM/SBC | 13/12/.2024 | for finance concurrence
4 | Moderanisation of SSPN station under Amrit Bharath Scheme | Cap | 195017 | Shortlisted | CPDE/SWR | 2024-08-11 | For Sanction
5 | Provision of Escalators in SBC division under Amrith Bhrath Scheme (Additional 23 Nos.) | Cap | 159249 | Shortlisted | CPDE/SWR | 2024-05-12 | Remarks for RB observation compiled and forwarded for further process
6 | Procurement of 575 Stainless steel benches (275 No. of 4-seater & 300 No. of 10-seater) at Railway stations over SBC Division. | Cap | 19360 | Shortlisted | Sr.DFM/SBC | 20-12-2024 | for vetting
7 | Kengeri~~Provision of one escalator on PF-4 of Kengeri railway station | Cap | 13710 | Shortlisted | Sr.DFM/SBC | 11/12//2024 | sent to Sr.DFM/SBC for vetting of revised amount
8 | Provision of water coolers on platforms over SBC Division to comply Minimum Essential Amenity Norms | Cap | 5491 | Shortlisted | Sr.DEE/SBc | 2024-04-05 | Remarks for Sr.DFM observation has to be compiled
9 | Modernization of Shravanabelagola (SBGA) Railway Station under Amrit Bharat Station Scheme | Cap | 150091 | Shortlisted | Sr.DFM/SBC | 23.12.2024 | For Further process
10 | Proposal for upgradation/modernization of infrastructure at Dharmapuri (DPJ) goods shed | Cap | 95613 | For Shortlisting | PCCM/SWR | 2024-09-12 | For shortlisting
11 | Replacing of low height platform shelters at PF-7/8, provision of shelter in open area between second entry building | Cap | 117220 | For Shortlisting | PCCM/SWR | 16-12-2024 | For Shortlisting
12 | Pro. new Foot over Bridge on PF 1 (B&C) connecting FOB 3 to metro FOB (Length-500m) | Cap | 264560 | For Shortlisting | DRM/SBC | 25-07-2024 | Requires RB Approval and NOC to be obtained from BMRCL. Letter sent to Sr.DEN/Co.ord , Sr.DEE/SBC on 26/10, 13/12 for estimates.
13 | Development of 2nd entry at YNK Station including Construction of Station building and other associated work | Cap | 498197 | For Shortlisting | DRM/SBC | 16-07-2024 | Note put for DRM Approval for inclusion of amenities
14 | SMVT - Widening of parcel handling platform to 20m at VPH siding, approach road at BYPL/KJM end and provision of Trolley path connecting PF- 4&5 to PF - 6&7 towards BAND end. | Cap | 27464 | For Shortlisting | DRM/SBC | 2024-03-09 | Note put for DRM Approval for change of plan head
15 | Reconstruction of existing station building on PF 1 not covered under station redevelopment work | Cap | 74093 | For Shortlisting | DRM/SBC | 2024-09-09 | returned from PCCM/SWR stating that "Not Shortlisted, As redevelopment work is going on, No other work may be proposed as concerned".
18 | Extension of existing FOB at Nidavanda (NDV) station on PF-1 side with Ramp | Cap | 28038 | For Shortlisting | DRM/SBC | 2024-08-10 | Returned from PCCM/SWR stating that minimum circulating area should be available for BO, Panel room and parking.
19 | Construction of FOB with Ramp & Provision of HL platform at PF No.1 at KIAT station | Cap | 57932 | For Shortlisting | PCCM/SWR | 23-12-2024 | Returned from CPDE/SWR to PCCM/SWR : As per PCE instruction, "extension of platform wall shall be done with pre-cast segments for faster progress as well as safety and to minimize inconvenience to the passengers. CPDE may write to all Sr.DENs for applying the same in all the future proposals subject to feasibility". Returned for incorporating above instructions in works proposal. Separate letter being issued from this office.
20 | Maralahalli~~Construction of High-level platform at MZV Station for the length of 400 meters at PF-1 & 2 | Cap | 40179 | For Shortlisting | PCCM/SWR | 2024-03-12 | For Shortlisting
21 | SBC Division - Provision of Quick coach watering system for PF 1 to 4 at SBC station | Cap | 62864 | For Shortlisting | DRM/SBC | 28.10.2024 | Returned from PCCM/SWR stating SBC being a terminal station, there is no shortage of time. Hence, Proposal returned.
22 | Sir.M.Visweswarayya Terminal- SBC Division - Provision of Quick coach watering system for all platforms at SMVB station | Cap | 48489 | For Shortlisting | DRM/SBC | 28.10.2024 | Returned from PCCM/SWR stating SMVB being a terminal station, there is no shortage of time. Hence, Proposal returned.
23 | Ballastless track with indigenous fastening system(BLT-IFS) For Loopline washable Apron for speed upto 50 kmph at Yards for a length of 16.8 km | Cap | 1428675 | For Shortlisting | DRM/SBC | 16-07-2024 | Returned from HQ
24 | Proposed construction of Skywalk (6 m wide) connecting Air concourse at PF 6 side to Yeswantpur Metro station. | Cap | 43544 | For Shortlisting | DRM/SBC | 20/09/2024 | Returned from PCCM/SWR stating This proposal involves coordination with 3 agencies , bengaluru metro , K-RIDE & CN-office .proper GAD to be prepared with sufficient clearance for movement of BUSES etc, to be made and get it approved. after that estimate to be prepared and resubmitted along with the proposal. Letter sent on 25/10, 13/12 to Dy.CE/CN/BNC for quordination between stake holders like BMRCL, KRIDE, Construction and other civil agencies