## Sheet1
Sl.no | Description | Status
1 | FOB Status - BID, | Tender opened on 9/12/24
2 | PCEV, PRNT, TPP,SZV | For GM approval - Currently with ADRM
4 | MDLL | LOA issued on 23.9.24
5 | SBC ( PF shelter 7 & 8) – Status | Tender to be called
6 | PF shelter gaps at SBC - Work proposal | Letter sent on 05.12.24. Estimates to be received from Sr.DEE/SrDEN
7 | New FOB from 3rd entry – Work proposal | Letter sent on 10.12.24 for Estimates
8 | New work - 3rd entry TTE Rest Room – SBC | Letter sent on 10.12.24 for Estimates
9 | TTE Rest room ( SMVB) - Construction - To follow up | Currently with Sr.DFM for Detailed estimate vetting
10 | Non standard PF shelter conversion to IRS type at SBC | TRD & Civil Estimate awaited. Reminder to be sent on 13.12.24
11 | Tender status - PF No.7/8 tender shelter work | Civil- Tender Awarded- WIP. Electrical Indent sent to HQ for Approval
12 | Civil works – PF No.7/8, 9/10, Metro Skywalk – work commencing, Lifts – Sr DEE/G | Civil- Tender Awarded- WIP. Electrical Indent sent to HQ for Approval
13 | Development of circulating area – To peruse | Provision of 4 autolanes of 3.6m wide with SS railings. Provision of 3 Taxi lanes
14 | Waiting hall renovation and shelter gap - PID – Left over
15 | Pay and use toilet ( SBC) – Issual of LOA on 21.10.24
16 | Passenger Amenities - Shortfall in platform length and platform shelter : – YNK – KQZ Section - Letter written to Sr DEN, Sr DEE & Sr DSTE for estimate on 04-09-2024 . | TRD & Civil Estimate yet to be recieved. Reminder sent on 07.12.24
17 | SBGA - Proposal for shortlisting of works under PH 53 with CPDE for shortlisting. | Cost revised to 15 Cr. Will be sent from GSU for shortlisting
18 | AEK , BLRR & HLE - Works taken up by K-RIDE . Letter sent from Sr DCM to GM/K RIDE copied to DRM and PCCM. Reply received from K-RIDE has been compiled and sent on 07-11-2024. (Nighil) | Reminder will be sent on 13.12.24
19 | BWT- 2nd entry connecting FOB to have escalator and lifts including building. Estimate received. Note to be put up for approval. | TRD Estimate pending. DCM spoke to DEE/TRD.
20 | SGWF (Sanctioned), PKD - Proposal pending with Railway Board . To follow up with Dy.Director/Railway Board.
21 | KDAG – With Finance (PCOM). | CPDE for further forwarding to RB
22 | PKD - Abstract estimate with cost sent to Railway Board on 04-09-2024 - Sanctioned. | Work alloted to GSU on 26.11.24. Letter written to CPM on 27.11.24 to take up work. Reminder will be sent on 16.12.24.
23 | Status of PH 53 towards renovation of Pay & Use Toilet and 3rd entry Booking office. (LOA issued on 21-10-2024) . | A letter will be written for early execution on 14.12.24
24 | Works to be proposed to Hqrs for deletion (35 works) - Letter sent on 04-09-2024 for early processing [ Three works deleted in the month of Nov 2024].
25 | Signage Boards –SBC-JTJ section ,DMM, MYS, SBC shelter --- Sanctioned. Detailed estimate under preparation. | SLP prepared. Review underway. ADSTE to sign.
26 | Beautification-Quotation power | 2 BQ's received. Detailed plan will be put up on 12/12/24
27 | YPR, SMVB -16mts - New -PID
28 | KIAT – New FOB with Ramp and PF extension | Currently with PCCM for shortlisting
29 | TK Station Development - Letter sent to CPM/GSU for inclusion of facilities in Master Plan – Estimate ready -84.41 Cr ; Same to be uploaded in IRPSM. [Sanctioned ]
30 | BAW Platform extension - LOA issued on 20-11-2024.
31 | 5 FOB status of SBC division sent from PCEE to CBE - Status of the proposal to be checked.
32 | Ketohalli and Nidaghatta – FOB . KHLL - LOA issued on 14-10-2024. NXH - LOA issued on 15-11-24. | WIP
33 | SBC Estimate – Alternate arrangements for escalator
34 | Landscape modification for circulating area works – SBC
35 | 3rd alternate FOB at third entry of SBC station .
36 | BMRCL - BNC metro connectivity proposal (26 Cr) – Travelator – 500 Mts (Estimate to be obtained) --Letter sent on 26-10-2024. A37:B37
37 | YPR – Metro connectivity (Drawing to be finalised by KRIDE, BMRCL & Construction) – To monitor
38 | BNC additional PF and modification of new station building - PH 53 Returned from HQrts-(Building work)
39 | KGI - PF shelter, parking and circulating area - Work under progress - Pillar extension work in progress at PF No.2&3. New station building exterior painting completed; Pay and Use Toilet at PF No.4 – Basement work in progress (12 mtrs from PF No.1 to 4 pending at Basement Level) KGI – Platform Shelter – TDC: 31.12.2024; To speak to Dy CE and get the updates on the works .
40 | Commissioning of Chakarlapalli station - To expedite with CN for early completion with provision of required amenities (Letter to be addressed to CN Unit with regard to amenities – coming or not coming) | PF 1 HLL completed. PF 2 WIP. Letter sent on 21.9.24
41 | PH 53 - YNK 2nd entry (Soft upgradation) - Electrical estimate yet to be received. (Electrical department have asked to furnish for full scope of work ). Note to be put up to DRM after receiving estimate.
42 | SSPN – Status of ABSS Works (19.5 Cr) | With hqrs for sanction.
44 | GBB - Work status under ABSS (To check with CPM/GSU) – Sanctioned. | Work alloted to GSU on 26.11.24. Letter written to CPM on 27.11.24 to take up work. Reminder will be sent on 16.12.24.
45 | ABSS (BAW) - SS Benches – With Hqrs for shortlisting.
46 | BAW Redevelopment with facilities like taxi,parking,commercial office,FOB,Escalator,
46 | ABSS Works - Parking at KPN, MLO (2nd Building), BWT & RMGM – Works completed. To be handed over for operation - To check with SSE/GSU likely date of handing over.
KGI - Parking lot – Under progress.
Amrit Bharat – Works Review (Contractors details to be obtained) - Yes
Amrit Bharat follow up works
1) Top priority - furniture procurement for KGI, KPN, MLO - GeM
2) KGI deficiencies:
a) Letter to PCCM seeking escalator in opposite direction in the existing FOB – Letter sent
b) Waiting hall General, ladies and executive waiting hall not yet shown. Master plan to be clarified
c) drop off zone at station to be clearly notified at KGI
d) Trolley path works to be done.
e) Platform repair works at PF-2/3, PF-4 to be checked and ensured
f) Second entry approach road lighting, station names and parking area to be developed at the time of handling over second entry along with fencing
g) Compound wall is being built at KGI pf-4.
One more work of pale fencing is also available with ABSS for execution
h) Reduction of concourse area to be clarified at KGI by ABSS
I) Dismantling of IRCTC and ATM at KGI to be expedited
Platform shelter (VB – BNC) - Estimate to be prepared [ Length requirements, Platform shelter, FOBs-3 – Matter to be discussed with Engg. Dept and proposal to be moved]
SBGA - Retiring room tariff to be fixed on par with the Trust ; Furniture provided - Tariff to be sent to Sr DFM for vetting (File moved in e-office for approval). – Completed
One existing camera at SMVB station to be shifted inside the Booking office ( Based on observations of Vigilance).
Liaison with BMTC for LED screen to feed Bus timings – CMI/Sumanth. TDC - 30.09.2024
Main parking boundary wall to be provided at WFD end of KJM station.
KJM - (To follow up - Nighil)
Three water coolers not in good condition, Letter addressed to Sr DEE .
Non-functioning of coach indication boards at PF No.2 - Letter sent to Sr DSTE.
Platform shelter leakage at PF No.4 - Letter sent to DEN/E on 05-09-2024.
Main parking boundary wall to be provided at WFD end. Letter to DEN/E
SMVB - Sensor at the urinals of pay and use toilet not functioning. Letter to be addressed to DEN/E . Letter addressed to Contractor of Pay and Use Toilet . (Nighil)
Portable Toilets close to SM ( at minor stations)/Halt Agent
Amrit Bharat – Works Review (Contractors details to be obtained) - Yes
Amrit Bharat follow up works
1) Top priority - furniture procurement for KGI, KPN, MLO - GeM