## Sheet1
Sl.no | Description | Status on 12.12.24 | Status on 16.12.24
1 | FOB Status - BID, | Tender opened on 9/12/24
2 | PCEV, PRNT, TPP,SZV | For GM approval - Currently with ADRM
3 | MDLL | LOA issued on 23.9.24
4 | SBC ( PF shelter 7 & 8) – Status | Tender to be called
5 | PF shelter gaps at SBC - Work proposal | Letter sent on 05.12.24. Estimates to be received from Sr.DEE/SrDEN
6 | New FOB from 3rd entry – Work proposal | Letter sent on 10.12.24 for Estimates
7 | New work - 3rd entry TTE Rest Room – SBC | Letter sent on 10.12.24 for Estimates
8 | TTE Rest room ( SMVB) - Construction - To follow up | Currently with Sr.DFM for Detailed estimate vetting
9 | Non standard PF shelter conversion to IRS type at SBC | TRD & Civil Estimate awaited. Reminder to be sent on 13.12.24
10 | Tender status - PF No.7/8 tender shelter work | Civil- Tender Awarded- WIP. Electrical Indent sent to HQ for Approval
11 | Civil works – PF No.7/8, 9/10, Metro Skywalk – work commencing, Lifts – Sr DEE/G | Civil- Tender Awarded- WIP. Electrical Indent sent to HQ for Approval
12 | Development of circulating area – To peruse | Provision of 4 autolanes of 3.6m wide with SS railings. Provision of 3 Taxi lanes
13 | Waiting hall renovation and shelter gap - PID – Left over
14 | Pay and use toilet ( SBC) – Issual of LOA on 21.10.24 | Letter will be written to take up work.
15 | Passenger Amenities - Shortfall in platform length and platform shelter : – YNK – KQZ Section - Letter written to Sr DEN, Sr DEE & Sr DSTE for estimate on 04-09-2024 . | TRD & Civil Estimate yet to be recieved. Reminder sent on 07.12.24
16 | SBGA - Proposal for shortlisting of works under PH 53 with CPDE for shortlisting. | Cost revised to 15 Cr. Will be sent from GSU for shortlisting
17 | AEK , BLRR & HLE - Works taken up by K-RIDE . Letter sent from Sr DCM to GM/K RIDE copied to DRM and PCCM. Reply received from K-RIDE has been compiled and sent on 07-11-2024. (Nighil) | Reminder will be sent on 13.12.24
18 | BWT- 2nd entry connecting FOB to have escalator and lifts including building. Estimate received. Note to be put up for approval. | TRD Estimate pending. DCM spoke to DEE/TRD.
19 | KDAG – With Finance (PCOM). | CPDE for further forwarding to RB
20 | PKD - Abstract estimate with cost sent to Railway Board on 04-09-2024 - Sanctioned. | Work alloted to GSU on 26.11.24. Letter written to CPM on 27.11.24 to take up work. Reminder will be sent on 16.12.24.
21 | Status of PH 53 towards renovation of Pay & Use Toilet and 3rd entry Booking office. (LOA issued on 21-10-2024) . | A letter will be written for early execution on 14.12.24
22 | Works to be proposed to Hqrs for deletion (35 works) - Letter sent on 04-09-2024 for early processing [ Three works deleted in the month of Nov 2024].
23 | Signage Boards –SBC-JTJ section ,DMM, MYS, SBC shelter --- Sanctioned. Detailed estimate under preparation. | SLP prepared. Review underway. ADSTE to sign.
24 | Beautification-Quotation power | 2 BQ's received. Detailed plan will be put up on 12/12/24
25 | YPR, SMVB -16mts - New -PID
26 | KIAT – New FOB with Ramp and PF extension | Currently with PCCM for shortlisting
27 | TK Station Development - Letter sent to CPM/GSU for inclusion of facilities in Master Plan -84.41 Cr . [Sanctioned ]
28 | BAW Platform extension - LOA issued on 20-11-2024. | Work to be started. Letter to take up work will be sent.
29 | Ketohalli and Nidaghatta – FOB . KHLL - LOA issued on 14-10-2024. NXH - LOA issued on 15-11-24. | WIP. Letter to take up work will be sent.
30 | SBC Estimate – Alternate arrangements for escalator
31 | BMRCL - BNC metro connectivity proposal (26 Cr) – Travelator – 500 Mts (Estimate to be obtained) --Letter sent on 26-10-2024.
32 | YPR – Metro connectivity (Drawing to be finalised by KRIDE, BMRCL & Construction) – To monitor | Letter written on 25.10.24 to Dy.CE/CN. Reminder will be sent on 13.12.24
33 | BNC additional PF and modification of new station building - PH 53 Returned from HQrts-(Building work)
35 | Commissioning of Chakarlapalli station - To expedite with CN for early completion with provision of required amenities (Letter to be addressed to CN Unit with regard to amenities – coming or not coming) | PF 1 HLL completed. PF 2 WIP. Letter sent on 21.9.24
36 | PH 53 - YNK 2nd entry (Soft upgradation) - Electrical estimate yet to be received. (Electrical department have asked to furnish for full scope of work ). Note to be put up to DRM after receiving estimate.
37 | SSPN – Status of ABSS Works (19.5 Cr) | With hqrs for sanction.
38 | GBB - Work status under ABSS (To check with CPM/GSU) – Sanctioned. | Work alloted to GSU on 26.11.24. Letter written to CPM on 27.11.24 to take up work. Reminder will be sent on 16.12.24.
39 | SS Benches – With Hqrs for shortlisting.
40 | BAW Redevelopment with facilities like taxi,parking,commercial office,FOB,Escalator, | Letter will be sent on 13.12.24
43 | Amrit Bharat – Works Review (Contractors details to be obtained) - Yes
44 | Amrit Bharat follow up works
45 | 1) Top priority - furniture procurement for KGI, KPN, MLO - GeM
46 | 2) KGI deficiencies:
47 | a) Letter to PCCM seeking escalator in opposite direction in the existing FOB – Letter sent | Letter written
48 | b) Waiting hall General, ladies and executive waiting hall not yet shown. Master plan to be clarified
49 | c) drop off zone at station to be clearly notified at KGI
50 | d) Trolley path works to be done.
51 | e) Platform repair works at PF-2/3, PF-4 to be checked and ensured
52 | f) Second entry approach road lighting, station names and parking area to be developed at the time of handling over second entry along with fencing
53 | g) Compound wall is being built at KGI pf-4.
54 | One more work of pale fencing is also available with ABSS for execution
55 | h) Reduction of concourse area to be clarified at KGI by ABSS
56 | I) Dismantling of IRCTC and ATM at KGI to be expedited
57 | Platform shelter (VB – BNC) - Estimate to be prepared [ Length requirements, Platform shelter, FOBs-3 – Matter to be discussed with Engg. Dept and proposal to be moved]
58 | SBGA - Retiring room tariff to be fixed on par with the Trust ; Furniture provided - Tariff to be sent to Sr DFM for vetting (File moved in e-office for approval). – Completed
59 | One existing camera at SMVB station to be shifted inside the Booking office ( Based on observations of Vigilance).
60 | Liaison with BMTC for LED screen to feed Bus timings – CMI/Sumanth. TDC - 30.09.2024
61 | Main parking boundary wall to be provided at WFD end of KJM station.
62 | KJM - (To follow up - Nighil)
63 | Three water coolers not in good condition, Letter addressed to Sr DEE .
64 | Non-functioning of coach indication boards at PF No.2 - Letter sent to Sr DSTE.
65 | Platform shelter leakage at PF No.4 - Letter sent to DEN/E on 05-09-2024.
66 | Main parking boundary wall to be provided at WFD end. Letter to DEN/E
67 | SMVB - Sensor at the urinals of pay and use toilet not functioning. Letter to be addressed to DEN/E . Letter addressed to Contractor of Pay and Use Toilet . (Nighil)
68 | Portable Toilets close to SM ( at minor stations)/Halt Agent
69 | Amrit Bharat – Works Review (Contractors details to be obtained) - Yes
70 | Amrit Bharat follow up works
71 | 1) Top priority - furniture procurement for KGI, KPN, MLO - GeM